## Project Plan
Stage | Task | Description | Status | Priority | Start Date | End Date | Owner
Requirements Analysis | Define Business Problem | Understand cybersecurity tracking challenges | Not Started | High | 2026-03-29 | 2026-03-29 | Hlekane
Requirements Analysis | Define Objectives | Monitor user activity and training effectiveness | Not Started | High | 2026-03-30 | 2026-03-30 | Hlekane
Requirements Analysis | Define Metrics | Events per user, phishing clicks, training completion | Not Started | Medium | 2026-03-31 | 2026-03-31 | Hlekane
Data Architecture Design | Design Star Schema | Create fact and dimension tables | Not Started | High | 2026-03-31 | 2026-03-31 | Hlekane
Data Architecture Design | Define Fact Table | Fact_User_Cyber_Event design | Not Started | High | 2026-03-31 | 2026-03-31 | Hlekane
Data Architecture Design | Define Dimensions | Dim_User, Dim_Date, Dim_Event_Type, etc. | Not Started | High | 2026-03-31 | 2026-03-31 | Hlekane
Data Architecture Design | Define Relationships | One-to-many relationships | Not Started | Medium | 2026-03-31 | 2026-03-31 | Hlekane
Project Initialisation | Naming Conventions | Define consistent naming standards | Not Started | Medium | 2026-03-31 | 2026-03-31 | Hlekane
Project Initialisation | Setup GitHub Repo | Create folders and structure | Not Started | High |  |  | Hlekane
Project Initialisation | Create Database | Cybersecurity_Awareness_DB | Not Started | High |  |  | Hlekane
Project Initialisation | Create Tables | Build dimensions and fact tables | Not Started | High |  |  | Hlekane
Data Creation | Generate Data | Use SQL inserts or CSV files | Not Started | High |  |  | Hlekane
Data Creation | Populate Tables | Insert 100+ dim and 300+ fact records | Not Started | High |  |  | Hlekane
Data Analysis | Write SQL Queries | Analyze events and trends | Not Started | High |  |  | Hlekane
Data Analysis | Extract Insights | Identify risky users | Not Started | Medium |  |  | Hlekane
Visualisation | Build Dashboard | Create charts in Tableau | Not Started | Medium |  |  | Hlekane